## Summary
Month | Create | Close | Assign | Resolve | Open | Wip | Resolved & Pending for User confirmation | Resolved & Pending for BA confirmation
2019-12 | 70 | 32 | 8 | 15 | 270 | 27 | 4 | 9
2019-11 | 42 | 39 | 20 | 11 | 223 | 29 | 0 | 3
2019-10 | 57 | 37 | 13 | 7 | 220 | 20 | 0 | 2
2019-09 | 50 | 34 | 14 | 10 | 200 | 13 | 3 | 0
2019-08 | 41 | 40 | 11 | 10 | 184 | 9 | 2 | 0
2019-07 | 51 | 86 | 18 | 19 | 183 | 8 | 0 | 2
2019-06 | 35 | 42 | 18 | 20 | 218 | 12 | 0 | 2
2019-05 | 56 | 37 | 21 | 23 | 225 | 14 | 1 | 2
2019-04 | 58 | 39 | 30 | 23 | 206 | 16 | 2 | 1
2019-03 | 62 | 50 | 19 | 16 | 187 | 9 | 0 | 1
2019-02 | 31 | 38 | 14 | 17 | 175 | 6 | 2 | 4
2019-01 | 50 | 53 | 19 | 20 | 182 | 9 | 0 | 2

## Resolve Detail
month | application | application_no | request_type | sub_type | severity | assign_dev_team_date | dev_resolved_time | dev_send_acknowledge_time | status | issue_description
2019-12 | eDeclaration | ITSR013951 | Appl Defect | Rules related | 4 | 2019-12-04 | 2019-12-04 | 2019-12-04 | Pending for User Prod Confirmation | STP系统，输入超过5个关联机构系统报错
2019-12 | eCashman | ITSR013662 | Request |  | 99 | 2019-09-03 | 2019-12-05 | 2019-09-04 | Pending for User UAT Confirmation | Invoice Not Printed check box 无效
2019-12 | CIRC | ITSR013967 | Request | data extracts | 99 | 2019-12-30 | 2019-12-30 | 2019-12-30 | Pending for BA Construction Process | Nov's CBIRC monthly report
2019-12 | PAW | ITSR013974 | Request | Data Patch | 99 | 2019-12-26 | 2019-12-26 | 2019-12-26 | Pending for BA Implement Process | Product code 020607，020608 下"意外身故及伤残"保障的class_peril_cd改成063
2019-12 | CIRC | ITSR013882 | Request | data extracts | 99 | 2019-11-22 | 2019-12-20 | 2019-11-22 | Pending for User UAT Confirmation | Oct's Circ report running
2019-12 | CIRC | ITSR013921 | Request | data extracts | 99 | 2019-12-30 | 2019-12-30 | 2019-12-30 | Pending for BA Construction Process | Monthly report and data extraction support
2019-12 | eCashman | ITSR013775 | Appl Defect | data entry | 1 | 2019-11-25 | 2019-12-06 | 2019-11-27 | Pending for BA Construction Process | ECASHMAN出现两个ID争用同一receipt no.，造成无法正常关bank。
2019-12 | eCashman | ITSR013827 | Appl Defect | Backend service | 1 | 2019-11-26 | 2019-12-04 | 2019-11-26 | Pending for Data Owner Production Approval | fix appscan security issue for eCashman
2019-12 | Intranet | ITSR013991 | Appl Defect | Reports related | 4 | 2019-12-26 | 2019-12-27 | 2019-12-27 | Pending for BA Construction Process | 运营部的事件跟踪报表无法正常导出“ 事件描述”
2019-12 | CIRC | ITSR013740 | Request | data extracts | 99 | 2019-12-30 | 2019-12-30 | 2019-12-30 | Pending for BA Construction Process | CIRC monthly report extraction and compliance related developments for Sep
2019-12 | CIRC | ITSR013787 | Request | data extracts | 99 | 2019-12-30 | 2019-12-30 | 2019-12-30 | Pending for BA Construction Process | CIRC monthly report extraction and compliance related developments for Sep.
2019-12 | S3B | ITSR013622 | Appl Enh | enhancement | 99 | 2019-12-12 | 2019-12-12 | 2019-12-12 | Pending for BA Implementation ConfirmClose | Win2k8Exit effort tracking only
2019-12 | PAW | ITSR014022 | Request | Data Patch | 99 | 2019-12-26 | 2019-12-26 | 2019-12-26 | Pending for User Prod Confirmation | A&H产品，广东分公司东莞营销部的美元币种付款通知书上的受款人信息有误，需要后台更新，正确的受款人名称应为“美亚财产保险有限公司广东分公司”
2019-12 | eCashman | ITSR013561 | Appl Enh | enhancement | 99 | 2019-07-19 | 2019-12-06 | 2019-07-19 | Pending for BA Construction Process | 在CPS打印发票页面里能看到Payor Name 这一项
2019-12 | S3B | ITSR013857 | Appl Enh | enhancement | 99 | 2019-11-27 | 2019-12-02 | 2019-11-27 | Closed | S3B PRM004报表，将保费值一栏中的错误币种符号删除

## Open Detail
month | application | application_no | request_type | sub_type | severity | assign_dev_team_date | dev_resolved_time | dev_send_acknowledge_time | close_date | status | issue_description
2019-12 | CIRC web Enquiry | ITSR014089 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | veracode issue fix
2019-12 | S3B | ITSR014079 | Request | reference data | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Tried to log off on Citrix Center but S3B do not work. Error 34303: The User ID was already logged on from another workstation.
2019-12 | CIRC PAI | ITSR014088 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | CIRC PAI monthly support for 201912
2019-12 | AML | ITSR014087 | Request | Data Patch | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | Supply organization customer information with KYC regulation in RDM/RDM_AML.
2019-12 | AML | ITSR014086 | Request | Data Patch | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | Supply organization customer information with KYC regulation in GOALD
2019-12 | AML | ITSR014085 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | for AML in Win2016 deploy only
2019-12 | ALPS | ITSR014084 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 请协助对系统进行相关设置使保单能ISSUE BOOKING
2019-12 | eDeclaration | ITSR014083 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 凭证没有显示保险计划-PBSH600019
2019-12 | AML | ITSR014080 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | AML系统可疑交易问题排查
2019-12 | PAW | ITSR014076 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 修改DM保障名称
2019-12 | S3B | ITSR014074 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 拉数据
2019-12 | PAW | ITSR014073 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 拉数据
2019-12 | AML | ITSR014070 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 因合规部门工作需要，需开通AML权限，恳请批准！
2019-12 | CIRC web Enquiry | ITSR014078 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 关于承保理赔信息客户自主查询情况2019年4季度的报告
2019-12 | eDeclaration - EL | ITSR014077 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | veracode scan fix
2019-12 | FARS | ITSR014069 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | New RI treaty has been approved by the BOD. Please update the XOL setting in FARS from Dec 1, 2019.
2019-12 | DMW | ITSR014067 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | DMW 保单（SH0F10001000017）增加多一个被保人后无法显示
2019-12 | S3B | ITSR014056 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 密码更新后，新旧秘密均无法使用，申请重置
2019-12 | eDeclaration | ITSR014053 | Appl Defect | Rules related | 4 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Veracode scan fix
2019-12 | S3B | ITSR014066 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | User ID was already logged from another workstation
2019-12 | eDeclaration | ITSR014065 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for User Confirmation | STP Quotation上出现“短期保险费批单”。这个批单STP系统不支持。需要修改STP quotation模板。
2019-12 | eCashman | ITSR014047 | Request | Data Patch | 99 | NULL | NULL | NULL | NULL | Pending for Data Owner Approval | EM45M00858 发票号：17697150 中Print Amt. 和Borrowed Amt.不一致，请将Debit Note No.203000 中Print Amt. 改为9076
2019-12 | AML | ITSR014052 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 目前可疑交易有几个类型，在系统逻辑设置上需要改进
2019-12 | ECM II | ITSR014051 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for Data Owner Approval | (1) Add a new ComBox under "Import Document" in ECM II. The ComBox name is "Encryption". And setup Claim Complex handlers' authority under the new ComBox. (2) The Claim Complex handlers name list add new staff "Yu Zhang".
2019-12 | PAW | ITSR014050 | Request | reference data | 99 | 2020-01-02 | 2020-01-02 | 2020-01-02 | NULL | Pending for BA Construction Process | 在指定BTA产品下增加急性病身故保障。
2019-12 | S3B | ITSR014049 | Request | reference data | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | S3B相同Department在不同Branch的描述不同，请修改-charge to csc
2019-12 | SRI | ITSR014048 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Renew FAC RI Code in System 2020
2019-12 | PAW | ITSR014043 | Request | reference data | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 在IPA产品下增加两个保障项目。
2019-12 | S3B | ITSR014046 | Request | User Access Mgmt | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | release s3b
2019-12 | Intranet | ITSR014045 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for User Confirmation | Add below 3 check box into GOOD account application and change the request name to Mobile service and account service. check box: 1、Company Phone 2、Company SIM card 3、Telecom Cost Reimbursement Apply
2019-12 | Intranet | ITSR014033 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | modify contract process for internet business contract, replace ITSR013996
2019-12 | eDeclaration - EL | ITSR014032 | Appl Defect | interface application processing | 4 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | endo premium display issue
2019-12 | S3B | ITSR014031 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Extract claims data
2019-12 | DMW | ITSR014030 | Appl Defect | Rules related | 4 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | Whitehat scan fix
2019-12 | PAW | ITSR014029 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | PAWeb GH产品的rating逻辑分析（现状：与手工录入保费不一致）
2019-12 | FARS | ITSR014042 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for Supervisor Approval | To Huabo: upload 2020B to CCR report
2019-12 | FARS | ITSR014041 | Request | reference data | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 2020 GOE allocation ratio
2019-12 | CIRC | ITSR014039 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Compare the existing CIRC SYS report with new rule report.
2019-12 | CIRC | ITSR014037 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Change the calculation rule for Travel and AH
2019-12 | ECM II | ITSR014034 | Appl Defect | Backend service | 4 | NULL | NULL | NULL | NULL | Pending for Data Owner Approval | WHITEHAT security fix - URL redirector abuse (HIGH)
2019-12 | DMW | ITSR014024 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 请协助统计北京分公司，2018-12-1到2019-11-30这段期间，DM系统中，北分的客户数和交易数
2019-12 | PAW | ITSR014023 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | PAWeb在录入美亚外籍人士医疗保险/美亚外籍人士团体医疗保险020120，020121，020220，020221这几个产品时，保费计算逻辑有误，需要后台更新计费逻辑
2019-12 | PAW | ITSR014022 | Request | Data Patch | 99 | 2019-12-26 | 2019-12-26 | 2019-12-26 | NULL | Pending for User Prod Confirmation | A&H产品，广东分公司东莞营销部的美元币种付款通知书上的受款人信息有误，需要后台更新，正确的受款人名称应为“美亚财产保险有限公司广东分公司”
2019-12 | DMW | ITSR014021 | Appl Defect | Rules related | 4 | NULL | NULL | NULL | NULL | Pending for User UAT Confirmation | 保单新增被保人后，系统无法显示保单详情
2019-12 | S3B | ITSR014028 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Receipt team说已经核销了保单GLSZ000122，但无法与S3B关联，查询S3B系统显示还没有核销，烦请协助，谢谢。
2019-12 | eDeclaration-Prl | ITSR014027 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | 请修改网上RMB DN的模板，不显示固定汇率。请修改网上DN的模板，highlight黄色。
2019-12 | EMMA | ITSR014026 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | 提取被保人超龄等因素需要被取消的保单清单，持招行借记卡代收的保单清单
2019-12 | S3B | ITSR014025 | Request | User Access Mgmt | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Reactive account
2019-12 | S3B | ITSR014012 | Request | User Access Mgmt | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | S3B显示被辞退，需要重置S3B账号
2019-12 | CIRC PAI | ITSR014007 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 测试SHIA的JDK 1.8兼容性
2019-12 | S3B | ITSR014006 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 无法登陆，显示用户已经离职
2019-12 | S3B | ITSR014011 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | add loss result as CIRC PAI requested
2019-12 | S3B | ITSR014010 | Request | User Access Mgmt | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Please active account and add CHO authorization
2019-12 | Intranet | ITSR014009 | Request | Configruation | 99 | NULL | NULL | NULL | 2020-01-01 | Closed | 修改更新report line
2019-12 | eCashman | ITSR013999 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for Data Owner Approval | Fix appscan 1 high issue of tracking id APS-2019-4630216
2019-12 | Intranet | ITSR013998 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | payment workflow error when reject after forward
2019-12 | Intranet | ITSR013997 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | appscan fix
2019-12 | Intranet | ITSR013996 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | add additional approval step for internet business contract.
2019-12 | eMarine | ITSR013986 | Request | Data Patch | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 东莞年度保单续保需要摊分业绩和佣金
2019-12 | Intranet | ITSR013991 | Appl Defect | Reports related | 4 | 2019-12-26 | 2019-12-27 | 2019-12-27 | NULL | Pending for BA Construction Process | 运营部的事件跟踪报表无法正常导出“ 事件描述”
2019-12 | FARS | ITSR013981 | Request | reference data | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | Need refresh FARS profile to support forecast data input of Y2020
2019-12 | CIRC | ITSR013967 | Request | data extracts | 99 | 2019-12-30 | 2019-12-30 | 2019-12-30 | NULL | Pending for BA Construction Process | Nov's CBIRC monthly report
2019-12 | PAW | ITSR013974 | Request | Data Patch | 99 | 2019-12-26 | 2019-12-26 | 2019-12-26 | NULL | Pending for BA Implement Process | Product code 020607，020608 下"意外身故及伤残"保障的class_peril_cd改成063
2019-12 | S3B | ITSR013970 | Appl Enh | enhancement | 99 | 2019-12-12 | NULL | 2019-12-12 | NULL | Pending for Dev. Team Process | According to Global OGIS communication, apply to set up two new products in S3B for Travel NAC(Risk Transfer) and Travel NAC(Risk Management) .
2019-12 | S3B | ITSR013965 | Enhancement |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Process | Apply Booking Product 'Travel NAC(Risk Transfer), Travel NAC(Risk Management)' Registration
2019-12 | S3B | ITSR013962 | Request | reference data | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | S3B LOB Code validation setting warning
2019-12 | PAW | ITSR013963 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | We will raise a ticket to ask for extracting data as following Booking data from 2019-11-1 to 2019-11-28 major line:02 A&H Minor line:01 & 02 & 09
2019-12 | S3B | ITSR013955 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 新增一个Recovery表在Data Export里面
2019-12 | eDeclaration | ITSR013951 | Appl Defect | Rules related | 4 | 2019-12-04 | 2019-12-04 | 2019-12-04 | NULL | Pending for User Prod Confirmation | STP系统，输入超过5个关联机构系统报错
2019-12 | eMarine | ITSR013949 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | issuing office display for suzhou
2019-12 | eDeclaration | ITSR013948 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 修改BTA凭证在按短期费率结算的计划下到期日的填写规则：凭证到期日设置为“不得早于大保单期满日期”，但承保天数不得超过1年，具体例子请看附件。 1. 只改动按短期费率结算的计划；按单日费率结算的计划维持原规则设置不变。 2. 此限制只针对外部客户，内部用户申报的计划到期日选择无限制。 3. 改动只在WBC/BTA2013产品下进行。
2019-12 | S3B | ITSR013946 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 前台同事反馈“乐依文半导体（东莞）有限公司”没有开票信息，经核查，2018年客户还开过专票，系统却没有了这个客户的VAT信息，用保单号和客户名都查不到
2019-12 | eMarine | ITSR013947 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Test Process | Fix eMarine veracode scan issue
2019-12 | AH Beijing IA | ITSR013938 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | BJIA Data extraction
2019-12 | FARS | ITSR013942 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | Amend AR reconciliation tools for share commission
2019-12 | S3B | ITSR013922 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | excel格式的报表出现乱码
2019-12 | CIRC | ITSR013921 | Request | data extracts | 99 | 2019-12-30 | 2019-12-30 | 2019-12-30 | NULL | Pending for BA Construction Process | Monthly report and data extraction support
2019-12 | S3B | ITSR013920 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 客户批量查询理赔，代理名称：友太安
2019-12 | CIRC web Enquiry | ITSR013917 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | A&H fix
2019-12 | eDeclaration | ITSR013916 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for User UAT Confirmation | STP BI中计划版本号需要更新为2019，目前为2018。若不修改，无法在后台系统中看出哪些使用新条款，哪些使用旧条款。
2019-12 | CIRC web Enquiry | ITSR013910 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | LIBERTY上传的Status结果是Failure
2019-12 | S3B | ITSR013909 | Appl Enh | enhancement | 99 | 2019-11-29 | NULL | 2019-11-29 | NULL | Pending for Dev. Team Process | S3B Claim system下，Feature页面新增Recovery Register Button
2019-12 | S3B | ITSR013908 | Appl Enh | enhancement | 99 | 2019-11-29 | NULL | 2019-11-29 | NULL | Pending for Dev. Team Process | S3B Claim system 新增AUD、CAD、GBP、SGD四国币种
2019-12 | CIRC web Enquiry | ITSR013892 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 【中保协保单验真二期】关于美亚保险的问题反馈记
2019-12 | CIRC PAI | ITSR013890 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | EAST for ZJ branch
2019-12 | CIRC PAI | ITSR013889 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | EAST for MC branch
2019-12 | CIRC PAI | ITSR013888 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | EAST support for SH branch
2019-12 | S3B | ITSR013895 | Request | reference data | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 要修改后台定义的payee name
2019-12 | S3B | ITSR013886 | Request | reference data | 99 | 2019-11-08 | 2019-11-19 | 2019-11-11 | NULL | Pending for BA Implement Process | 苹果理赔不能release
2019-12 | Intranet | ITSR013879 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | bank payment request form添加Vendor地址
2019-12 | CIRC | ITSR013882 | Request | data extracts | 99 | 2019-11-22 | 2019-12-20 | 2019-11-22 | NULL | Pending for User UAT Confirmation | Oct's Circ report running
2019-12 | Intranet | ITSR013877 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | AICS approval settings change, cost will be charge to 3M22
2019-12 | Seamless Integration | ITSR013874 | Appl Enh | enhancement | 99 | 2019-11-04 | NULL | 2019-11-05 | NULL | Pending for Dev. Team Process | Seamless grouping change to improve CIRC report
2019-12 | Seamless Integration | ITSR013873 | Request | Data Patch | 99 | 2019-11-04 | NULL | 2019-11-05 | NULL | Pending for Dev. Team Process | Data patch to fix the tmall premium issue
2019-12 | AML | ITSR013870 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | AML系统中可疑文件只能上传，不能编辑。请增加可以编辑功能，如编辑，删除等。谢谢。
2019-12 | Seamless Integration | ITSR013867 | Request | Data Patch | 99 | NULL | NULL | NULL | NULL | Pending for BA Implement Process | update the grouping status to ‘Gourp_success’
2019-12 | ALPS | ITSR013866 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 修改Producer code状态的提醒功能
2019-12 | S3B | ITSR013865 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 关于开展银行保险机构侵害消费者权益乱象整治工作的通知/2019年“巩固治乱象成果 促进合规建设”的年度自查工作的数据导出
2019-12 | S3B | ITSR013864 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 代理途径：旅云保，一共需查询135个理赔案件进度
2019-12 | eMarine | ITSR013851 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 付款通知书上添加以下备注信息（Charge to F&A-Grant）： 由于所投保单为外币计价的外币保单，如选择人民币支付上述保费的，则所适用的汇率应以贵司支付上述保费当月首个工作日中国人民银行公布的人民币中间汇率为准。 As the policy is denominated in foreign currency, if CNY is chosen to pay the above premium, the applicable exchange rate shall be based on the CNY intermediate exchange rate announced by the People's Bank of China on the first working day of the month when your company pays the above premium.
2019-12 | S3B | ITSR013850 | Appl Enh | enhancement | 99 | 2019-11-28 | NULL | 2019-11-28 | NULL | Pending for Dev. Team Process | 外币的付款通知书上添加以下备注信息（Charge to F&A-Grant）： 由于所投保单为外币计价的外币保单，如选择人民币支付上述保费的，则所适用的汇率应以贵司支付上述保费当月首个工作日中国人民银行公布的人民币中间汇率为准。 As the policy is denominated in foreign currency, if CNY is chosen to pay the above premium, the applicable exchange rate shall be based on the CNY intermediate exchange rate announced by the People's Bank of China on the first working day of the month when your company pays the above premium.
2019-12 | CIRC | ITSR013843 | Appl Enh | enhancement | 99 | 2019-12-30 | NULL | 2019-12-30 | NULL | Pending for Dev. Team Process | Get Insured count from SDI field
2019-12 | CIRC | ITSR013842 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | Get CIRC SYS statistic data from eDCR directly
2019-12 | CIRC | ITSR013841 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | Get CIRC SYS statistic data from TIPS directly
2019-12 | CIRC | ITSR013840 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | Get CIRC SYS statistic data from DM directly
2019-12 | TWS | ITSR013839 | Appl Enh | enhancement | 99 | 2019-10-17 | NULL | 2019-10-17 | NULL | Pending for Dev. Team Process | Fix the producer load issue
2019-12 | TWS | ITSR013838 | Request | Producer Update | 99 | 2019-10-17 | NULL | 2019-10-17 | NULL | Pending for Dev. Team Process | Regression test for travel new product
2019-12 | Seamless Integration | ITSR013837 | Appl Enh | enhancement | 99 | 2019-10-18 | NULL | 2019-10-18 | NULL | Pending for Dev. Team Process | Fix the cancellation issue
2019-12 | Seamless Integration | ITSR013836 | Request | data extracts | 99 | 2019-10-18 | NULL | 2019-10-18 | NULL | Pending for Dev. Team Process | Data extracting for policy commission
2019-12 | Seamless Integration | ITSR013835 | Request | data extracts | 99 | 2019-10-18 | NULL | 2019-10-18 | NULL | Pending for Dev. Team Process | Data extracting for policy relationship
2019-12 | Seamless Integration | ITSR013834 | Request | reference data | 99 | 2019-10-18 | NULL | 2019-10-18 | NULL | Pending for Dev. Team Process | SDI regression test for travel new product bulk book
2019-12 | Seamless Integration | ITSR013832 | Request | reference data | 99 | 2019-10-18 | NULL | 2019-10-18 | NULL | Pending for Dev. Team Process | eCashman data analysis for travel new product bulk book
2019-12 | Seamless Integration | ITSR013833 | Appl Enh | enhancement | 99 | 2019-10-18 | NULL | 2019-10-18 | NULL | Pending for Dev. Team Process | S3B impact analysis for travel new product bulk book
2019-12 | ECM II | ITSR013828 | Appl Defect | interface application processing | 4 | NULL | NULL | NULL | NULL | Pending for Data Owner Approval | 公共盘的文件的File to ECM Claims的功能失效
2019-12 | Seamless Integration | ITSR013831 | Appl Enh | enhancement | 99 | 2019-10-17 | NULL | 2019-10-17 | NULL | Pending for Dev. Team Process | Downstream impact analysis and regression test for Travel business new product launch.
2019-12 | Seamless Integration | ITSR013830 | Request | data extracts | 99 | 2019-10-17 | NULL | 2019-10-17 | NULL | Pending for Dev. Team Process | Data extracting for billing and grouping for 2019 data analysis.
2019-12 | S3B | ITSR013826 | Request | reference data | 99 | 2019-11-27 | NULL | 2019-11-27 | NULL | Pending for Dev. Team Process | S3B 里 MA71000225 B/OMS信息空白，请协助查原因。----charge to MAS
2019-12 | eCashman | ITSR013827 | Appl Defect | Backend service | 1 | 2019-11-26 | 2019-12-04 | 2019-11-26 | NULL | Pending for Data Owner Production Approval | fix appscan security issue for eCashman
2019-12 | eDeclaration | ITSR013813 | Appl Enh | enhancement | 99 | 2019-11-13 | 2019-11-29 | 2019-11-13 | NULL | Pending for BA Implement Process | Per veracode scan result, upgrading spring library is necessary.
2019-12 | eDeclaration-Prl | ITSR013823 | Appl Enh | enhancement | 99 | 2019-12-30 | NULL | 2019-12-30 | NULL | Pending for Dev. Team Process | fix source code scan (Veracode) security issue in eDeclaration Prl +Spring Upgrade
2019-12 | CIRC PAI | ITSR013815 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | EAST data report submission for SH/ZJ/MC, requested by SH and ZJ CBRIC
2019-12 | eDeclaration - EL | ITSR013812 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | code scan fix
2019-12 | PAW | ITSR013800 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | add additional field for user to input insured count
2019-12 | TWS | ITSR013799 | Request | reference data | 99 | 2019-10-18 | NULL | 2019-10-18 | NULL | Pending for Dev. Team Process | refresh the existing coverage mapping for downstream BJIA and WebEnquiry.
2019-12 | Seamless Integration | ITSR013798 | Appl Enh | enhancement | 99 | 2019-10-17 | 2019-11-22 | 2019-10-17 | NULL | Pending for BA Implement Process | Enhance the seamless integration logic. The existing logic is to group all premium to a single GOALD coverage belong to Accident. However the actual policies has health and property part. After change the premium will be broken down to different coverage and process to downstreams.This is mandetory for CIRC compliance
2019-12 | CIRC | ITSR013801 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Change the calculation rule for Travel and AH
2019-12 | Goald | ITSR013792 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Axon - MDM Investigate
2019-12 | S3B | ITSR013788 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 修改/增加S3B系统中Group BTA产品理赔部份的coverage code和description。
2019-12 | CIRC | ITSR013787 | Request | data extracts | 99 | 2019-12-30 | 2019-12-30 | 2019-12-30 | NULL | Pending for BA Construction Process | CIRC monthly report extraction and compliance related developments for Sep.
2019-12 | CIRC PAI | ITSR013776 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | SH and ZJ CBRIC data extract
2019-12 | CIRC web Enquiry | ITSR013773 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | for Non auto policy inquiry issue
2019-12 | eDeclaration | ITSR013772 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Mybenefit UAT环境替换新增和减员费率表
2019-12 | eCashman | ITSR013775 | Appl Defect | data entry | 1 | 2019-11-25 | 2019-12-06 | 2019-11-27 | NULL | Pending for BA Construction Process | ECASHMAN出现两个ID争用同一receipt no.，造成无法正常关bank。
2019-12 | eDeclaration | ITSR013768 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 在STP revamping上线前，对于过度阶段的有效报价，经过与Debbie还有IT商议，在正式上线前在系统中一次性拉出过度阶段有效报价的关键信息，以便后台人工出单。所需成本较低，望批准。
2019-12 | S3B | ITSR013770 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for User Confirmation | 中民保险40个理赔记录
2019-12 | eCashman | ITSR013764 | Request | Data Patch | 99 | 2019-09-17 | 2019-09-18 | 2019-09-18 | NULL | Pending for User Confirmation | 导出的借票在allocation界面无法找到，invoice enquiry查询该借票已核销
2019-12 | S3B | ITSR013762 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for User Confirmation | 友太安保险70多个理赔记录
2019-12 | eCashman | ITSR013757 | Appl Defect | data entry | 1 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 在开具题述保单的已销账booking时，在保费查询页面及发票开具页面显示的合计金额是RMB39811.70，但在发票开具页面的金额确认显示为RMB39811.69，与客户实际支付相差0.01，
2019-12 | C-link | ITSR013760 | Appl Enh | enhancement | 99 | 2019-12-27 | NULL | 2019-12-27 | NULL | Pending for Dev. Team Process | 26 CGN affiliated entities need to be screened in Clink by weekly.
2019-12 | ALPS | ITSR013753 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | alps系统中个人KYC信息不完整，需要进行系统change.
2019-12 | Intranet | ITSR013748 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | update S3B user form to 2.7
2019-12 | Intranet | ITSR013750 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Build the User ID applying (including create new account and disable existing account) workflow of 美亚一路通 system to intranet, the data owner is Karen
2019-12 | CIRC | ITSR013740 | Request | data extracts | 99 | 2019-12-30 | 2019-12-30 | 2019-12-30 | NULL | Pending for BA Construction Process | CIRC monthly report extraction and compliance related developments for Sep
2019-12 | ALPS | ITSR013734 | Appl Defect | interface application processing | 4 | NULL | NULL | NULL | NULL | Pending for User Confirmation | 批单booking不能成功issue，总是有报错提示，详情请参考附件的沟通邮件，谢谢
2019-12 | CIRC PAI | ITSR013738 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | monthly support for Aug
2019-12 | eCashman | ITSR013737 | Request | reference data | 99 | 2019-09-25 | NULL | 2019-09-26 | NULL | Pending for Dev. Team Process | 红冲发票不能正常取号
2019-12 | CIRC web Enquiry | ITSR013733 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | win 2016 upgrade for web enquiry
2019-12 | TWS | ITSR013728 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Cancellation Rule - when transfer to TWS, Cancellation policy should be with \1.But now all cancel policy with \1 are failed transfer with NB not exist.
2019-12 | TWS | ITSR013727 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Duplicate ID for different insured on same policy - LSHBU71326\1 7/9 Endorsement - LSHCA20772\1 7/25 Cancellation
2019-12 | CIRC | ITSR013725 | Request | data extracts | 99 | 2019-09-09 | 2019-10-08 | 2019-09-09 | NULL | Pending for BA Test Process | August Circ Monthly Report
2019-12 | FARS | ITSR013723 | Request | data extracts | 99 | 2019-09-23 | 2019-10-17 | 2019-09-23 | NULL | Pending for BA Implement Process | Support of GOE Budget and GPW budget of 2020.
2019-12 | FARS | ITSR013722 | Appl Enh | enhancement | 99 | 2019-09-23 | NULL | 2019-09-23 | NULL | Pending for Dev. Team Process | BPC upload report function development.
2019-12 | CIRC web Enquiry | ITSR013717 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | fix IA interface II issues
2019-12 | Intranet | ITSR013716 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | add vendor report and payment report for monthly requests
2019-12 | eCashman | ITSR013708 | Request | Configruation | 99 | 2019-08-21 | 2019-09-20 | 2019-08-21 | NULL | Pending for User UAT Confirmation | 东莞普通发票不能正常取号
2019-12 | S3B | ITSR013705 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | win2k8exit project - S3B
2019-12 | eMarine | ITSR013692 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for Data Owner Production Approval | 修改付款通知书招商银行上海东方支行营业地址为如下: 中国（上海）自由贸易试验区世纪大道1192号L1层032号商铺、L2层033号商铺 L1, Shop No. 032, L2, Shop No. 033 No. 1192, Century Avenue, Shanghai, China
2019-12 | eDeclaration | ITSR013689 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for Supervisor Approval | 增加业务员代码-0113029331（WBSH500703）
2019-12 | eCashman | ITSR013688 | Request | Data Patch | 99 | 2019-11-25 | NULL | 2019-11-27 | NULL | Pending for Dev. Team Process | WBBJ500092 TR 36/37销账无法summit
2019-12 | eDeclaration | ITSR013687 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for Supervisor Approval | 增加业务员代码-0040108001-SH
2019-12 | Intranet | ITSR013677 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 将my payment request 分页
2019-12 | Intranet | ITSR013676 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 查找并且修复%2f在URL里引起的apache转译问题
2019-12 | eCashman | ITSR013662 | Request |  | 99 | 2019-09-03 | 2019-12-05 | 2019-09-04 | NULL | Pending for User UAT Confirmation | Invoice Not Printed check box 无效
2019-12 | CIRC PAI | ITSR013655 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | monthly support for july
2019-12 | FARS | ITSR013651 | Appl Enh | program defect | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Veracode Scan Fix
2019-12 | Goald | ITSR013650 | Appl Enh | enhancement | 99 | 2019-07-31 | NULL | 2019-08-01 | NULL | Pending for Dev. Team Process | Axon - Whole DB Migration to Standard server
2019-12 | eMarine | ITSR013641 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for Data Owner Approval | Catch referral approval rate for total_rate in report.
2019-12 | AML | ITSR013636 | Request | data extracts | 99 | 2019-08-13 | 2019-08-28 | 2019-08-13 | NULL | Pending for User UAT Confirmation | provide data for GZ PBOC
2019-12 | S3B | ITSR013633 | Appl Enh | enhancement | 99 | 2019-08-22 | NULL | 2019-08-22 | NULL | Pending for Dev. Team Process | Further update ITSR013469 all line authority logic in S3B
2019-12 | CIRC | ITSR013631 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for User Confirmation | CIRC Report of June
2019-12 | AH Beijing IA | ITSR013625 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Upgrade to windows 2016 & jdk 1.8
2019-12 | Intranet | ITSR013620 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | manually resend jamed email
2019-12 | S3B | ITSR013622 | Appl Enh | enhancement | 99 | 2019-12-12 | 2019-12-12 | 2019-12-12 | NULL | Pending for BA Implementation ConfirmClose | Win2k8Exit effort tracking only
2019-12 | CIRC | ITSR013615 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for User UAT Confirmation | 根据北京银保监《关于调整部分报告形式和强化主监管员制度的通知》和《关于加强保险服务民营、小微企业 有关工作的通知》，北分将从6月起新增2个月报和1个季报，相比统信数据， 需要更多和insured name和coverage等相关的详细信息
2019-12 | CIRC PAI | ITSR013617 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | policy extract and upload logic update.
2019-12 | FARS | ITSR013606 | Appl Enh | enhancement | 99 | 2019-07-02 | 2019-07-03 | 2019-07-02 | NULL | Pending for BA Implement Process | Enhance and adjust budget capture of 2020 function
2019-12 | FARS | ITSR013605 | Appl Enh | enhancement | 99 | 2019-07-02 | 2019-07-08 | 2019-07-02 | NULL | Pending for BA Test Process | Develop upload GOE input file function(IT, Project, Admin, Sal)
2019-12 | ALPS | ITSR013602 | Appl Enh | enhancement | 99 | 2019-12-27 | 2019-10-08 | 2019-12-27 | NULL | Pending for Dev. Team Process | ALPS remarks 添加销售信息提示框
2019-12 | AML | ITSR013599 | Appl Enh | enhancement | 99 | 2019-06-24 | 2019-08-14 | 2019-06-24 | NULL | Pending for User Prod Confirmation | AML系统里添加批量上传证明材料的功能, 并按照branch显示相关信息
2019-12 | CIRC PAI | ITSR013601 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | for CIRC PAI monthly support
2019-12 | Intranet | ITSR013588 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | fix the delegation for group assign
2019-12 | Intranet | ITSR013587 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | fix the delegation function in payment process
2019-12 | Intranet | ITSR013586 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | fix the delegation rule in ITSR process
2019-12 | CIRC PAI | ITSR013585 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | fix veracode scan issue.
2019-12 | CIRC PAI | ITSR013566 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | monthly report
2019-12 | Intranet | ITSR013565 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Pega 8.2 upgrade research
2019-12 | eCashman | ITSR013561 | Appl Enh | enhancement | 99 | 2019-07-19 | 2019-12-06 | 2019-07-19 | NULL | Pending for BA Construction Process | 在CPS打印发票页面里能看到Payor Name 这一项
2019-12 | CIRC PAI | ITSR013544 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | fix the validation rule, part 1
2019-12 | EMMA | ITSR013528 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 将数据库授权从public组改到userall组：DMBATCH和WSMBATCH
2019-12 | Intranet | ITSR013515 | Request | Configruation | 99 | 2019-05-08 | 2019-06-10 | 2019-05-08 | NULL | Pending for BA Construction Process | to investigate on the delegation logic on major process
2019-12 | CIRC web Enquiry | ITSR013505 | Appl Defect | Backend service | 4 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 【中保协保单验真二期】关于美亚保险的问题反馈记录——IACHINA2019-042500012 修改日期格式， 险种名称 以及保单类别
2019-12 | CIRC PAI | ITSR013508 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | CIRC PAI daily support and data analysis
2019-12 | CIRC | ITSR013507 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for User Confirmation | April CIRC Monthly Report
2019-12 | S3B | ITSR013502 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for Supervisor Approval | ANH产品下在S3B开案选取对应的feature时有对应的benefit code
2019-12 | ALPS | ITSR013500 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for Supervisor Approval | 修改ARSH000403的正数保费booking不含VAT
2019-12 | S3B | ITSR013495 | Appl Enh | enhancement | 99 | 2019-06-11 | 2019-09-06 | 2019-06-11 | NULL | Pending for User Prod Confirmation | RPA process encounter deadlock issue from time to time when create FNOL
2019-12 | Goald | ITSR013471 | Request | data extracts | 99 | 2019-06-10 | 2019-06-12 | 2019-06-10 | NULL | Pending for BA Construction Process | SHIA recover historical data upload
2019-12 | Intranet | ITSR013461 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | take up TPRM role, please help to set up PR and contract approral role related to TPRM
2019-12 | Intranet | ITSR013460 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | take up TPRM role, please help to set up PR and contract approral role related to TPRM
2019-12 | eMarine | ITSR013456 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for User Prod Confirmation | Logic update for Cancel Request( cert. which waited for cancel)
2019-12 | Intranet | ITSR013454 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | changes on the PO balance enhancement
2019-12 | CIRC web Enquiry | ITSR013452 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 承保理赔信息客户自主查询情况2019年1季度的报告
2019-12 | Intranet | ITSR013450 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Take up TPRM role, pls help to set up PR and contract approval role related to TPRM.
2019-12 | CIRC PAI | ITSR013418 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | 2月CIRC PAI上报数据与统信数据对比
2019-12 | CIRC PAI | ITSR013417 | Request | Configruation | 99 | 2019-05-08 | 2019-05-10 | 2019-05-08 | NULL | Pending for BA Construction Process | 中保信下发表间数据校验自查及情况说明
2019-12 | S3B | ITSR013405 | Appl Enh | enhancement | 99 | 2019-03-29 | 2019-04-03 | 2019-03-29 | NULL | Pending for BA Implement Process | 在付款文件中的收款人字段的两端加入双引号，付款文件就不会因为含有生僻字无法上传
2019-12 | Intranet | ITSR013398 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | system did not popup the list for historical ebanking voucher report
2019-12 | Intranet | ITSR013397 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | out of memory error
2019-12 | ALPS | ITSR013391 | Appl Defect | interface application processing | 4 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 当批单生效日与保单生效日不一致时，ALPS不会把批单保费计入总保费来判断“客户总保费是否超过RMB200,000.00”。 请帮忙更新判断KYC的逻辑，使ALPS判断KYC的条件更新为本年度总保费，谢谢。
2019-12 | Intranet | ITSR013390 | Appl Enh | enhancement | 99 | 2019-04-09 | 2019-05-16 | 2019-04-10 | NULL | Pending for User Confirmation | Update comment into risk assessment in ITSR, and make it mandatory with dropdown/pre-filled value for user to proceed.
2019-12 | Intranet | ITSR013387 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | payment flow error, for PO payment and reject by CFO/COO, workflow will not return to initial step.
2019-12 | Intranet | ITSR013385 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | reset password issue on first time login
2019-12 | CIRC PAI | ITSR013384 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | daily support and regulator request research
2019-12 | S3B | ITSR013378 | Appl Enh | enhancement | 99 | 2019-03-29 | 2019-04-03 | 2019-03-29 | NULL | Pending for User Prod Confirmation | 如果理赔款包含VAT ,PP voucher的逻辑必须跟leger的一致，COA40910010 按VAT选择的赔付币种记账
2019-12 | CIRC PAI | ITSR013365 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | application support for 201902, mainly focus on data validation batch 1/2
2019-12 | Intranet | ITSR013328 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | take up TPRM role, please help to set up PR and contract approval role related to TPRM
2019-12 | CIRC web Enquiry | ITSR013324 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 1. 在Web enquiry的ID index表内，将DM保单中所有状态不是取消的，且是身份证类型证件的，patch进去 2. 在Web enquiry内，将DM保单，expire date是1900的，状态非cancel的，抓到filter表里 3. 在抓取DM保单时，如果状态是cancel，取DM里的cancel_date作为保单的expire date 4. 在web enquiry的filter表内，每天delete的job要排除DM的保单，避免删除 5. 中保协接口里，要保证filter表内DM保单，expire date是1900的有效保单，能被查询到，返回报文里expire date传空，取消的保单按正常逻辑处理 6. Lixiong研究下DM的cancel 保单SH02J000001324是怎么被web enquiry抓取到的
2019-12 | CIRC PAI | ITSR013312 | Request | data extracts | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | daily support and other related tasks in Jan 2019
2019-12 | eDeclaration | ITSR013299 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for User Confirmation | BTA产品下新增3个全新保障，以及对4个现有保障进行改动。
2019-12 | Intranet | ITSR013305 | Appl Enh | enhancement | 99 | 2019-02-25 | 2019-03-14 | 2019-02-25 | NULL | Pending for BA Construction Process | fix the reset password issue for default account
2019-12 | CIRC web Enquiry | ITSR013294 | Request | Data Patch | 99 | 2019-02-12 | 2019-02-19 | 2019-02-12 | NULL | Pending for BA Implement Process | 【中保协保单验真二期】关于美亚保险的问题反馈记录——IACHINA2019-011000017
2019-12 | FARS | ITSR013264 | Request | reference data | 99 | 2019-01-18 | 2019-02-22 | 2019-02-22 | NULL | Pending for User UAT Confirmation | FARS GPW template update for FY2019
2019-12 | eDeclaration | ITSR013255 | Request | Data Patch | 99 | 2018-12-20 | 2018-12-20 | 2018-12-20 | NULL | Pending for User Confirmation | 客户申报时系统一直显示失败，目前查看系统保单发生多个重复上传，且不能取消，请协助查看原因并取消重复的申报记录，谢谢。
2019-12 | ALPS | ITSR013257 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 改造需求：系统自动fill-in“统一征信代码”、企业类型、地址等信息。
2019-12 | S3B | ITSR013249 | Appl Enh | enhancement | 99 | 2019-07-18 | NULL | 2019-07-18 | NULL | Pending for Dev. Team Process | 1.在2个工作日内，系统评出新建业以及续保客户的务风险评估结果 2.对于重新评级和定期人工复核，实现系统留痕
2019-12 | AML | ITSR013248 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 1.系统每天发邮件给合规部，列示目前中高风险客户名单 2.对中高风险客户，系统提醒每半年进行重新评级
2019-12 | Goald | ITSR013236 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | P&L automation
2019-12 | PAW | ITSR013233 | Request | Data Patch | 99 | 2019-02-18 | 2019-02-14 | 2018-12-12 | NULL | Pending for User UAT Confirmation | 请修改WBSH501161的management code为05
2019-12 | FARS | ITSR013215 | Request | Data Patch | 99 | 2018-12-26 | 2018-12-26 | 2018-12-26 | NULL | Pending for User UAT Confirmation | 2019 reinsurance exit treaty rate setting
2019-12 | CIRC PAI | ITSR013202 | Request | Configruation | 99 | 2019-01-24 | 2019-02-18 | 2019-01-24 | NULL | Pending for BA Construction Process | 1. 11月的错误数据的补报（1。RDM效验，2。Sinosoft的效验，3。保信数据效验） 2. 总结保信数据效验哪些需要添加到Sinosoft的规则中 3. 性能调优
2019-12 | Intranet | ITSR013187 | Appl Enh | enhancement | 99 | 2019-01-24 | 2019-02-11 | 2019-02-11 | NULL | Pending for BA Implement Process | systmen enhancment of contract review
2019-12 | Intranet | ITSR013146 | Appl Enh | enhancement | 99 | 2018-11-29 | 2019-02-22 | 2018-11-30 | NULL | Pending for BA Implement Process | 新加一个role，在payment/batchpayment最终approve之后，如果等值人民币于等于100万，则给这个role发邮件提醒大额交易。
2019-12 | Intranet | ITSR013145 | Appl Enh | enhancement | 99 | 2019-01-25 | 2019-01-25 | 2019-01-25 | NULL | Pending for BA Implement Process | 只针对inovice no相同的情况，提交时做提醒，已经提交过相同金额的payment(payment no)，并且不允许提交。 对于相同vendor，无发票，金额相同的payment，提交时做提醒，已经提交过相同金额的payment(payment no)，用户确定后仍允许提交。
2019-12 | Intranet | ITSR013144 | Appl Enh | enhancement | 99 | 2019-03-25 | 2019-05-16 | 2019-03-25 | NULL | Pending for BA Test Process | 在payment/batch payment界面，如果是PO payment，在界面计算并且显示所有历史上link到此PO的payment和（注意币种），并且提是用户，如果到达总金额了，需要勾选final payment，如果未到达总金额，用户也勾选了final payment则需要提示，并输入remark(新增)。
2019-12 | S3B | ITSR013102 | Appl Enh | enhancement | 99 | 2018-10-11 | 2018-10-23 | 2018-10-12 | NULL | Pending for BA Implement Process | adjust PCI masking rule
2019-12 | Intranet | ITSR013060 | Appl Enh | enhancement | 99 | 2018-11-29 | 2018-12-17 | 2018-11-30 | NULL | Pending for BA Construction Process | pls. help to set two items for epayment & Concur separately. The link pls. refer to attached mail. Thanks. ePayment ● Manual ● Approval limit Concur ● Manual ● Reimbursement limit
2019-12 | CIRC web Enquiry | ITSR013047 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | 中保协微信公众号取值调整
2019-12 | ALPS | ITSR013032 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 改进ALPS系统的分期功能
2019-12 | PAW | ITSR013010 | Appl Enh | enhancement | 99 | 2019-07-18 | 2018-11-09 | 2018-09-28 | NULL | Pending for BA Implementation ConfirmClose | 在保单模板中增加保费币种
2019-12 | eDeclaration | ITSR012988 | Request | Data Patch | 99 | 2019-01-07 | 2018-08-21 | 2018-08-20 | NULL | Pending for User Confirmation | U/W建议优化各渠道使用的部分保障描述："员工慰问探访"，“商业设备租赁费用补偿”描述做改动。因此需要将改后的结果同步到STP中。改动详情将邮件形式发送给Lisa Zeng参考。
2019-12 | CIRC web Enquiry | ITSR012985 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Construction Process | web enquiry job optimize Duplicate Key confict分析 特殊字符处理 新的office code做mapping 每天的批次做分割，避免性能问题 解析XML先记录条数，记录XML-DB 结果比较 XML字段review,是否有统计错误 替换现有的VB程序(这点先做评估）
2019-12 | TWS | ITSR012972 | Appl Enh | enhancement | 99 | 2019-01-08 | 2019-01-18 | 2019-01-08 | NULL | Pending for BA Construction Process | 针对死锁的情况建立重送机制
2019-12 | FARS | ITSR012967 | Request | Configruation | 99 | NULL | NULL | NULL | NULL | Pending for User UAT Confirmation | fields extend & claim VAT source change
2019-12 | eMarine | ITSR012944 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Test Process | eMarine S/N is always effective for external client ID
2019-12 | FARS | ITSR012934 | Request | Configruation | 99 | 2018-08-03 | 2018-09-12 | 2018-08-03 | NULL | Pending for User UAT Confirmation | VAT-FAC报告，被保险人名字和发票抬头都为乱码
2019-12 | Seamless Integration | ITSR012925 | Request | Configruation | 99 | 2018-08-06 | 2018-08-09 | 2018-08-07 | NULL | Pending for BA Test Process | Please create a new branch in TIPS, following are the details: Branch Code: CH English Name: China Home Ofice Chinese Name: 总部 Office Code associated with CH Branch: 80
2019-12 | TWS | ITSR012886 | Request | Data Patch | 99 | 2018-11-19 | 2018-11-19 | 2018-11-19 | NULL | Pending for BA Construction Process | Please create a new branch in TWS, following are the details: Branch Code: CH English Name: China Home Ofice Chinese Name: 总部 Office Code associated with CH Branch: 80
2019-12 | FARS | ITSR012863 | Request | data extracts | 99 | 2018-08-10 | 2018-08-13 | 2018-08-13 | NULL | Pending for User UAT Confirmation | FARS 2019 budget module set-up
2019-12 | Intranet | ITSR012799 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 修改ebanking生成SPDB文件的日期字段为报销款 银行账号前加0
2019-12 | Intranet | ITSR012770 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | 1. Payment提交界面增加PO balance查询功能，能够列出PO总金额，link到此PO的所有payment no及金额，剩余balance，并且支持导出功能。 2. 对于没有剩余balance或者在tolerance范围的PO，自动将payment页面的final payment置为Y，无论Y或者N，都加入强制comments。 3. Intranet可以从Computron得到最新的PO状态（open/close），以用来同步（实时/batch）
2019-12 | FARS | ITSR012678 | Request | Data Patch | 99 | 2018-09-26 | 2018-10-09 | 2018-09-26 | NULL | Pending for User UAT Confirmation | Please help to release the changing of current status of receivable report in FARS . For more changing information,please refer to the attached email
2019-12 | FARS | ITSR012643 | Request | Configruation | 99 | 2018-04-17 | 2018-04-18 | 2018-04-18 | NULL | Pending for User UAT Confirmation | Setting a FARS job to send reminding email to target person automatically.
2019-12 | EMMA | ITSR012599 | Appl Defect | user interface | 4 | 2018-03-21 | 2018-03-29 | 2018-03-21 | NULL | Pending for User Confirmation | DM Data Extract Error Branch: JS,ZJ 无法回盘的REJ文件
2019-12 | eDeclaration - EL | ITSR012528 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Implement Process | system enhancement
2019-12 | ALPS | ITSR012463 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for User UAT Confirmation | add a new product for TC by adding A to 200116.
2019-12 | ALPS | ITSR012456 | Appl Defect | interface application processing | 4 | 2018-01-03 | 2018-01-03 | 2018-01-03 | NULL | Pending for User Confirmation | PTDG000069续保无法booking
2019-12 | eMarine | ITSR012422 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Add new clauses and update existing clauses
2019-12 | ALPS | ITSR012396 | Appl Defect | interface application processing | 4 | NULL | NULL | NULL | NULL | Pending for User Confirmation | CBC销账后不能正常issue
2019-12 | ECM II | ITSR012378 | Appl Enh | enhancement | 99 | 2017-12-27 | 2018-01-04 | 2017-12-28 | NULL | Pending for User Prod Confirmation | Case的 handler可以在myinbox中的Claim folder设置一个Folder或一个文件可以被哪些user打开。user的选择以Branch/LOB/Role的新式显示，指定后的folder或文件需要被标注已经限制打开。
2019-12 | eCashman | ITSR012338 | Request | reference data | 99 | 2019-03-15 | 2019-04-03 | 2019-03-15 | NULL | Pending for User UAT Confirmation | CBC RMB 的 booking，在S3B中显示不了保费、Paid Status以及保费确认时间、保单生成时间，请帮忙解决，谢谢 GLGZ000273
2019-12 | Intranet | ITSR012283 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | update organization chart
2019-12 | eCashman | ITSR012242 | Appl Enh | enhancement | 99 | 2018-09-26 | 2018-09-26 | 2018-09-26 | NULL | Pending for User UAT Confirmation | eCashman enhancement request
2019-12 | eCashman | ITSR012222 | Request | Data Patch | 99 | 2018-09-26 | 2018-10-19 | 2018-09-26 | NULL | Pending for User Confirmation | S3B显示的invoice no无法与eCashman同步
2019-12 | eMarine | ITSR012191 | Request | Data Patch | 99 | NULL | NULL | NULL | NULL | Pending for Data Owner Production Approval | 申请修复广州地区，无法显示作废原因且没审批的作废申请。具体需修复数据，请见附件截屏。谢谢！
2019-12 | eMarine | ITSR011986 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | Book remark for negative Miscellaneous Booking
2019-12 | eDeclaration - EL | ITSR011982 | Appl Enh | enhancement | 99 | 2017-11-20 | 2017-08-13 | 2017-08-10 | NULL | Pending for Dev. Team Process | 捷保系统经常出现“请联系管理员”或“请不要重复提交”的错误提醒。请帮忙调整系统，使申报系统能根据上传名单所存在的问题，有针对性的显示出来，以便客户能更有效和快捷的查找无法正常申报的原因并进行相应处理，谢谢。
2019-12 | FARS | ITSR011921 | Appl Enh | enhancement | 99 | NULL | NULL | NULL | NULL | Pending for BA Implement Process | Open an window to let users download FARS estimate data by branch. Multi branches can be selected when run the reports
2019-12 | eCashman | ITSR011889 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for BA Initial Process | WBSZ500510 Endt No.165
2019-12 | ECM II | ITSR011753 |  |  | 0 | NULL | NULL | NULL | NULL | Pending for Supervisor Approval | update file2ecm for claims configuration file
2019-12 | ECM II | ITSR011674 | Appl Enh | enhancement | 99 | 2017-05-17 | 2017-06-01 | 2017-05-17 | NULL | Pending for BA Construction Process | We can not search out the resigned user ID within half year in batch handler function now, so we need to remove the user ID checking logic from this function to meet user's requirement.